## Dashboard
Backend Engineering Roadmap: Progress Dashboard
Project start date | 2026-10-10
Topics included | 14
Topics completed | 1
Total tasks (included topics) | 85
Tasks done | 20
Overall progress | 23.53%
Total planned weeks | 30
Projected finish date | 2027-05-07
Progress by phase
Phase | Topics included | Total tasks | Tasks done | % Done
1 Foundations | 5 | 29 | 18 | 62.07%
2 Core API | 4 | 24 | 2 | 8.333%
3 Security & Quality | 3 | 19 | 0 | 0%
4 Production | 2 | 13 | 0 | 0%
How to use
1. Roadmap sheet: set Include? to Yes/No for each topic. Optional topics (Redis/Celery, CI/CD) start as No; switch to Yes to add them.
2. Change Est. weeks if a topic takes you longer or shorter; dates shift automatically and skip excluded topics.
3. Tasks sheet: update Status as you work. Roadmap % Done, Status and this dashboard update by themselves.
4. Add your own tasks at the bottom of the Tasks sheet using the topic's Step number.
5. Finish each topic's practice project before moving on; the Capstone (Step 16) ties everything together.

## Roadmap
Backend Engineering Roadmap (Python / FastAPI)
Step | Phase | Topic | What to learn | Practice project / deliverable | Source | Level | Include? | Est. weeks | Total tasks | Done tasks | % Done | Status | Start date | Target end | Suggested resources | Notes
1 | 1 Foundations | Python | Functions, OOP, modules, exception handling | CLI to-do app with file/JSON persistence | Original | Core | Yes | 3 | 7 | 6 | 85.71% | In Progress | 2026-10-10 | 2026-10-30 | Python docs tutorial; Real Python
2 | 1 Foundations | Git & Command Line | Terminal navigation, commits, branches, GitHub | Push your Python project to GitHub with a README | Added | Core | Yes | 1 | 4 | 0 | 0% | Not Started | 2026-10-31 | 2026-11-06 | Pro Git book (free); GitHub Docs
3 | 1 Foundations | SQL | SELECT, INSERT, UPDATE, DELETE, JOIN | Design and query a small store/library database | Original | Core | Yes | 2 | 6 | 6 | 100% | Completed | 2026-11-07 | 2026-11-20 | SQLBolt; Mode SQL tutorial
4 | 1 Foundations | Database | SQLite, relationships, primary and foreign keys, indexes | Normalized schema with FKs and indexes, used from Python | Original | Core | Yes | 2 | 6 | 3 | 50% | In Progress | 2026-11-21 | 2026-12-04 | SQLite docs; Python sqlite3 docs
5 | 1 Foundations | HTTP | Requests, responses, HTTP methods, status codes | Call 3 public APIs with curl, Postman and httpx | Original | Core | Yes | 1 | 6 | 3 | 50% | In Progress | 2026-12-05 | 2026-12-11 | MDN HTTP guide; httpx docs
6 | 2 Core API | FastAPI | Routes, endpoints, request handling, response models | Notes/Todo REST API with full CRUD | Original | Core | Yes | 3 | 8 | 2 | 25% | In Progress | 2026-12-12 | 2027-01-01 | FastAPI official tutorial
7 | 2 Core API | Pydantic | Data validation and serialization | Create/Update/Read schemas for your API | Original | Core | Yes | 1 | 5 | 0 | 0% | Not Started | 2027-01-02 | 2027-01-08 | Pydantic docs
8 | 2 Core API | ORM | SQLAlchemy and database integration | Replace in-memory storage with SQLAlchemy models | Original | Core | Yes | 2 | 6 | 0 | 0% | Not Started | 2027-01-09 | 2027-01-22 | SQLAlchemy 2.0 tutorial
9 | 2 Core API | PostgreSQL & Migrations | Postgres, Alembic migrations, pagination, query tuning | Move API to Postgres with Alembic migrations | Added | Recommended | Yes | 2 | 5 | 0 | 0% | Not Started | 2027-01-23 | 2027-02-05 | PostgreSQL tutorial; Alembic docs
10 | 3 Security & Quality | Authentication | Password hashing, JWT, OAuth2 | Register/login with JWT and protected routes | Original | Core | Yes | 2 | 7 | 0 | 0% | Not Started | 2027-02-06 | 2027-02-19 | FastAPI security tutorial; OWASP cheat sheets
11 | 3 Security & Quality | Testing | Pytest and API testing | Test suite with 80%+ coverage | Original | Core | Yes | 2 | 6 | 0 | 0% | Not Started | 2027-02-20 | 2027-03-05 | Pytest docs; FastAPI testing guide
12 | 3 Security & Quality | API Design, Logging & Security | REST conventions, logging, error format, OWASP basics | Harden your API: logging, error format, CORS, limits | Added | Recommended | Yes | 2 | 6 | 0 | 0% | Not Started | 2027-03-06 | 2027-03-19 | OWASP API Top 10; Microsoft REST guidelines
13 | 4 Production | Caching & Background Tasks | Redis, background jobs, queues | Cache a slow endpoint; send email via background job | Added | Optional | No | 2 | 5 | 0 | 0% | Excluded | - | - | Redis University; Celery/ARQ docs
14 | 4 Production | Deployment | Docker, Linux basics, and cloud deployment | Live deployed API with HTTPS | Original | Core | Yes | 3 | 6 | 0 | 0% | Not Started | 2027-03-20 | 2027-04-09 | Docker docs; DigitalOcean/Render/Railway guides
15 | 4 Production | CI/CD | GitHub Actions: test, lint, build, deploy | Pipeline that tests and deploys on every push to main | Added | Optional | No | 1 | 4 | 0 | 0% | Excluded | - | - | GitHub Actions docs
16 | 4 Production | Capstone Project | Build and ship a complete backend end to end | Portfolio-ready API (e.g. blog, e-commerce, task manager) | Added | Core | Yes | 4 | 7 | 0 | 0% | Not Started | 2027-04-10 | 2027-05-07 | Your own repo + README
|  | Total (included topics) | [5 empty] | 30 | 85 | 20 | 23.53%
Formulas:
Start date = IF([Include?]="Yes",Dashboard!$C4+(SUMIFS(J5:[Est. weeks],I5:[Include?],"Yes")-[Est. weeks])*7,"-")
Target end = IF([Include?]="Yes",[Start date]+[Est. weeks]*7-1,"-")

## Tasks
Task Checklist
Step | Topic | Task | Status | Date done | Notes
1 | Python | Write functions with default/keyword args, *args and **kwargs | Done
1 | Python | Practice lists, dicts, sets and comprehensions | Done
1 | Python | Build classes with inheritance and dunder methods | Done
1 | Python | Organize code into modules/packages; use venv and pip | Done
1 | Python | Handle errors with try/except and custom exceptions | Done
1 | Python | Read and write files and JSON | Done
1 | Python | Finish the CLI to-do app project | Not Started
2 | Git & Command Line | Navigate terminal: cd, ls, grep, pipes | Not Started
2 | Git & Command Line | Init a repo; stage, commit, view history | Not Started
2 | Git & Command Line | Create and merge branches; resolve a merge conflict | Not Started
2 | Git & Command Line | Use .gitignore; push project to GitHub with README | Not Started
3 | SQL | SELECT with WHERE, ORDER BY, LIMIT | Done
3 | SQL | INSERT, UPDATE, DELETE safely (with WHERE) | Done
3 | SQL | INNER and LEFT JOINs across 3 tables | Done
3 | SQL | GROUP BY, HAVING and aggregate functions | Done
3 | SQL | Write subqueries | Done
3 | SQL | Solve 20 practice problems | Done
4 | Database | Create tables with data types and constraints | Done
4 | Database | Define primary/foreign keys; model 1-1, 1-N, M-N | Done
4 | Database | Normalize a schema to 3NF | Not Started
4 | Database | Add indexes; compare with EXPLAIN QUERY PLAN | Not Started
4 | Database | Use the sqlite3 module from Python | Done
4 | Database | Use transactions (commit/rollback) | Not Started
5 | HTTP | Learn request/response structure, headers and body | Done
5 | HTTP | Understand methods and idempotency (GET/POST/PUT/PATCH/DELETE) | Done
5 | HTTP | Memorize status code families (2xx/3xx/4xx/5xx) | Done
5 | HTTP | Call APIs with curl and Postman | In Progress
5 | HTTP | Use requests or httpx in Python | Not Started
5 | HTTP | Understand cookies, CORS and HTTPS basics | Not Started
6 | FastAPI | Install FastAPI + uvicorn; explore /docs | Done
6 | FastAPI | Path, query and body parameters | Not Started
6 | FastAPI | Build CRUD endpoints (in-memory first) | Done
6 | FastAPI | Use response_model and status codes | Not Started
6 | FastAPI | Raise HTTPException; custom error handling | Not Started
6 | FastAPI | Dependency injection with Depends | Not Started
6 | FastAPI | Split routes with APIRouter; project structure | Not Started
6 | FastAPI | Understand async vs sync endpoints | Not Started
7 | Pydantic | Define BaseModel with type hints | Not Started
7 | Pydantic | Add Field constraints and validators | Not Started
7 | Pydantic | Separate Create, Update and Read schemas | Not Started
7 | Pydantic | Nested models and serialization (model_dump) | Not Started
7 | Pydantic | Manage settings with pydantic-settings and .env | Not Started
8 | ORM | Define SQLAlchemy models | Not Started
8 | ORM | Set up engine, session and get_db dependency | Not Started
8 | ORM | Implement CRUD with ORM queries | Not Started
8 | ORM | Model relationships (relationship, back_populates) | Not Started
8 | ORM | Avoid N+1 queries (joinedload/selectinload) | Not Started
8 | ORM | Wire ORM into FastAPI endpoints | Not Started
9 | PostgreSQL & Migrations | Run Postgres (Docker) and learn psql basics | Not Started
9 | PostgreSQL & Migrations | Switch SQLAlchemy to Postgres | Not Started
9 | PostgreSQL & Migrations | Create and apply Alembic migrations (up/down) | Not Started
9 | PostgreSQL & Migrations | Add pagination and filtering to list endpoints | Not Started
9 | PostgreSQL & Migrations | Use EXPLAIN ANALYZE and add an index | Not Started
10 | Authentication | Hash passwords with bcrypt or argon2 | Not Started
10 | Authentication | Build register and login endpoints | Not Started
10 | Authentication | Issue and verify JWT access tokens | Not Started
10 | Authentication | Protect routes with a dependency | Not Started
10 | Authentication | Implement OAuth2 password flow in FastAPI | Not Started
10 | Authentication | Add role-based access (admin/user) | Not Started
10 | Authentication | Learn refresh tokens and social login (concept) | Not Started
11 | Testing | Pytest basics: fixtures, parametrize | Not Started
11 | Testing | Test endpoints with TestClient | Not Started
11 | Testing | Use a test DB via dependency_overrides | Not Started
11 | Testing | Test auth flows (login, protected routes) | Not Started
11 | Testing | Mock external calls | Not Started
11 | Testing | Generate coverage report and reach 80% | Not Started
12 | API Design, Logging & Security | Apply REST naming, versioning, pagination conventions | Not Started
12 | API Design, Logging & Security | Add structured logging | Not Started
12 | API Design, Logging & Security | Keep secrets in env vars; never commit them | Not Started
12 | API Design, Logging & Security | Configure CORS; add rate limiting and input limits | Not Started
12 | API Design, Logging & Security | Review OWASP API Top 10 against your app | Not Started
12 | API Design, Logging & Security | Add global exception handlers with one error format | Not Started
13 | Caching & Background Tasks | Learn Redis basics (keys, TTL) | Not Started
13 | Caching & Background Tasks | Cache a read-heavy endpoint | Not Started
13 | Caching & Background Tasks | Use FastAPI BackgroundTasks | Not Started
13 | Caching & Background Tasks | Run a queued job with Celery or ARQ | Not Started
13 | Caching & Background Tasks | Implement rate limiting with Redis | Not Started
14 | Deployment | Linux basics: permissions, processes, systemd, ssh | Not Started
14 | Deployment | Write a Dockerfile (multi-stage) | Not Started
14 | Deployment | Run app + DB with docker-compose | Not Started
14 | Deployment | Deploy to a cloud host (Render/Railway/AWS/VPS) | Not Started
14 | Deployment | Set up Nginx reverse proxy and HTTPS | Not Started
14 | Deployment | Manage env vars/secrets; add a /health endpoint | Not Started
15 | CI/CD | Run pytest on every push with GitHub Actions | Not Started
15 | CI/CD | Add lint/format checks (ruff, black) | Not Started
15 | CI/CD | Build and push Docker image | Not Started
15 | CI/CD | Auto-deploy on merge to main | Not Started
16 | Capstone Project | Choose project; write requirements and ERD | Not Started
16 | Capstone Project | Implement models and migrations | Not Started
16 | Capstone Project | Implement CRUD + auth endpoints | Not Started
16 | Capstone Project | Write tests (80%+ coverage) | Not Started
16 | Capstone Project | Dockerize and deploy | Not Started
16 | Capstone Project | Write README with API docs and live demo link | Not Started
16 | Capstone Project | Add project to GitHub profile / portfolio | Not Started